| Presidents Goals Priority #4 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Ensure strong, mission-centric operations in the Provost’s Office | Chaouki Abdallah |  | On-going | Reorganized the Academic Affairs leadership team and responsibilities in an effort to focus our effort and resources on the academic mission Additional Information: click here Reorganization of Administrative Services, Budget/Financial Affairs and Data Analysis is underway. Organizational and staffing changes/enhancements will be implemented during the Spring 2012 semester. |
| Develop and implement an allocation plan for the $2M set aside for faculty hires in FY11/12 budget | Chaouki Abdallah Kate Henz |  | Fall 2011 | Complete In July the Provost Office called for proposals from the Main Campus Academic Affairs Deans and by September Deans were notified of approvals to search and hire 20 new tenure/tenure track faculty. The Provost Office received nearly $2.5 million, or 32 FTE, in requests. Leveraging available resources and anticipating additional faculty lines in future years, we awarded just over $1.6 million, or 20 FTE, in new faculty. |
| Increase by 10% each year the number of classes taught by tenure or tenure-track faculty | Chaouki Abdallah Michael Dougher Jane Slaughter Deans | Mark Chisholm – I could provide a report on current teaching loads of senior faculty | On-going | One way to accomplish this goal is to increase the number of tenure & tenure-track faculty. Therefore, the goal is to make the case to increase T & TT faculty by 20 per year for the foreseeable future. Additionally, we will start a campaign with our senior faculty to encourage them to teach one freshman or sophomore course every two years |
| Complete the planning for an Honors College and the future of University College | Michael Dougher |  | Spring 2012 | Good progress has been made with respect to a proposal from the Provost's Office to the Faculty Senate and Regents for the creation of an Honors College. A task force has been at work for the past three months exploring the options, complexities and costs associated with the establishment of an Honors College, and a formal proposal will be delivered to the Faculty Senate early in the spring semester. Honors college report: click here |
| Continue development strategies, with benchmarks, to improve retention & graduation rates. Benchmarks should be targeted to match the graduation rates of the average of peer universities | Greg Heileman | Mark Chisholm – we can provide extensive comparative data of graduation rates of peers, and a breakdown of rates by various demographic variables. | On-going | We have continued to work with the Graduation Express team in order to address our six-year graduation rates. We have produced a first-order model that predicts a six-year graduation rate of 45.58% for the 2006 cohort (next year), and 46.05% for the 2007 cohort (spreadsheet attached). This model takes the students that have already graduated in the cohort into account, and then uses the average of the historical graduation rates in order to predict how many reaming in the cohort will graduate within six years. The HLIC model for graduation rates, based on student demographics, predicts that our graduation rates should be approximately 47%. One possible measure of the success of the Graduation Express project will be the degree to which we can improve our graduate rates over the baseline rates that the first-order model predicts. Note: The Graduation Project has only been in effect for one year, so it’s had minimal impact on the historical graduation data. We can provided a more detailed report of our efforts in this area at the next meeting if that is something the committee would like to see. |
| Complete the planning for equity and inclusion initiatives, including an assessment of the Office of Equity & Inclusion. | Chaouki Abdallah Michael Dougher Jane Slaughter Jozi DeLeon |  | Academic Year 2011/12 Spring 2012 | The Diversity Council has been formed and has begun meeting. A team is currently being formed to evaluate the Office of Equity & Inclusion. For more information please click here |
| Regents A/SA & Research Goals |  |  |  |  |
| Goal 1 – Student Success |  |  |  |  |
| Peer benchmark on student success outcomes | Greg Heileman Curtis Porter | Mark Chisholm | Mark Chisholm – we are building a peer database with comparative data for a variety of comparison institutions. | Have begun to identify peer institutions according to type (e.g., flagship, Carnegie classification, etc.) and student demographics. Continuing to work on “closing the loop” between SLOs and improvements in student achievement. The curriculum portion of this has been missing. The idea is to more directly tie curriculum improvements to the SLOs. We have initially targeted the general education core. We have redently worked with Student Services in order to identify SLOs for new student orientation. |
| Address assessment of Student Learning Outcomes as directly related to improvements in student achievement and capability | Greg Heileman Deans | Tom Root |  |  |
| Goal 2 – Build Faculty Strength |  |  |  |  |
| Goals/Priorities | Chaouki Abdallah Michael Dougher Jane Slaughter Natasha Kolchevska Deans | Melissa Vargas Kate Moore Deans | Early Spring 2011 | Plan to hire 20 new faculty this upcoming year. The deans were asked to develop a multi-year hiring plans, but specifics will depend on the progress and ideas developed in the Academic plan. |
| Recruitment | Michael Dougher Jane Slaughter Jozi DeLeon Deans Dept. Chairs | Deans | Early Spring 2011 | See above. |
| Budget wedge into the future | Curtis Porter Kate Henz Deans |  | Ongoing | Discussions have begun with the Provost and Deans to develop a long term plan for utilization of new resources in Academic Affairs |
| Adjuncts – what role in the Academic Plan (Pay, benefits, capability) | Chaouki Abdallah Michael Dougher Deans |  |  | In progress-policies being developed by Sr VP Dougher. |
| Goal 3 – Understand full picture of student expenses |  |  |  |  |
| Amount of financial assistance available, on average | Terry Babbitt |  | 11.2011: baseline data available 1.2012: Completed | This data is currently available |
| Student work income available, on average | Terry Babbitt |  | 11.2011: baseline data available 1.2012: Completed | This data is currently available |
| Breakout of where student tuition and fees go (including 30% tax) | Curtis Porter |  |  | Presentations to ASA & R Committee by both Budget Office and Provost’s Office ( 12/7) |
| Lottery Scholarships: what are the benefits and options to consider? | Terry Babbitt Mark Saavedra |  | 9.2011: initial position and UNM data presented to LFC and LESC 11.2011: unified position with NMSU prior to legislative session 1.2012: track legislative intentions through Government Relations Office | This is continuously monitored. |
| Track progress on the tuition and fee policy planning for the FY13 budget, especially the criteria used | Curtis Porter |  |  | Provost staff is represented on the Budget Office Tuition and Fee Committee |
| Goal 4 – Establish a clear picture of the Research enterprise |  |  |  | For additional information click here |
| Size & Costs | Julia Fulghum |  | Ongoing |  |
| Strong areas (current and potential) | Julia Fulghum |  | Ongoing |  |
| Partnerships | Julia Fulghum |  |  | SNL, AFRL, and LANL partnerships being developed and strengthened |
| Payoffs in all relevant terms – especially to other parts of the academic enterprise | Julia Fulghum |  |  |  |
| Establish a five to ten year plan to increase internally funded research in order to support faculty in the humanities and junior faculty. | Jane Slaughter |  |  | Considerable effort already for external funding; Spring semester 2012 initiation of the internal assessments |
| Goal 5 – Assessment |  |  |  |  |
| Address HLC report concerns about assessment | Greg Heileman | Tom Root |  | Holding weekly meeting with Tom regarding the on-going roll-out of Tk20 across campus, and departmental compliance w.r.t. reporting assessment data. |
| Identify “responsibility” for implementation and analysis of results of assessment of core competencies and use assessment results for improving student learning | Chaouki Abdallah Greg Heileman |  |  | Just starting. |
| Goal 6 – Academic Plan | Chaouki Abdallah Geraldine Forbes Curtis Porter Melissa Vargas | Mark Chisholm – we provided a first cut of background data, and can provide data support to any of the subgroups as needed. | On-going | First major initiative: Creation of five work groups co-chaired by Deans or senior administrators in Academic Affairs - Value/Value Systems & Comparative Advantage (Co-chairs Douglas Brown & Rita Martinez-Purson) - Improving Undergraduate Education (Co-chairs Kevin Washburn, Mark Peceny, Donald Godwin, Kate Krause) - New Institutional Models (Co-chairs Michael Dougher, Catalin Roman) - Research & Graduate Education (Co-chairs Julia Fulghum, Gary Harrison) - Financial Analysis (Co-chairs Curtis Porter, Martha Bedard) Work group co-chairs were asked to take nominations from ASUNM, GPSA, Faculty Senate and Staff Council and then populate the remaining membership of their work groups ensuring broad representation from across campus while also keeping the size manageable. As their charge, co-chairs were asked to take the broad themes and add, detract, and shape the topics based on the original feedback from UCAP members and, most importantly, the ideas of their work groups and develop initial thoughts. At this time, most of the work groups have already met at least once and are beginning the process of assessing the major issues and developing their concepts. Draft papers are due to the Provost’s office by March 15. Second major initiative: Public lecture series A key feature of our academic planning process is a series of public lectures by scholars and administrators of repute on major issues of U.S. higher education. We kicked off this series on January 23 with Donald Randel, President of the Andrew Mellon Foundation, former president of the University of Chicago and long-time faculty member and administrator from Cornell University. His talk, “Higher Education in the U.S.: Divesting in the Future, Divesting in Ourselves” was well received by the campus community and had the intended impact of stimulating important conversations about our future. If you missed the talk, the audio recording can be accessed on the Academic Affairs website. The next lecture will be on Friday, February 10 by Jim Ellis current Dean of the Marshall School of Business at the University of Southern California |
| Goal 7 – Recognizing and incentivizing excellent teaching. What do faculty need to succeed? | Chaouki Abdallah Michael Dougher Jane Slaughter Natasha Kolchevska Deans |  |  | Discussions with AP Heileman, Slaugther, and Dougher about placing incentives for good teaching. |
| Goal 8 – Honors College communication and implementation plan | Michael Dougher Natasha Kolchevska |  |  | Good progress has been made with respect to a proposal from the Provost's Office to the Faculty Senate and Regents for the creation of an Honors College. A task force has been at work for the past three months exploring the options, complexities and costs associated with the establishment of an Honors College, and a formal proposal will be delivered to the Faculty Senate early in the spring semester. Honors college report: click here |
| Goal 9 – Attracting high achieving in-state and out-of-state students | Greg Heileman | Terry Babbit |  | Not yet started. |
| Quality/Value | Terry Babbitt Natasha Kolchevska |  | Domestic: 12.1.2012 Evaluate current National Merit applicants 2.2012: offer as many merit awards as possible Ongoing: continue communication plan for high achievers; support Honors College concept 4.2012: evaluate and redefine “high achieving” and necessary investment to recruit a nucleus of these students who can “push the needle” of student success metrics. | We are currently in the middle of communication strategies and recruitment for the 2012 class and on schedule. It is appropriate to re-evaluate the strategies every year during the spring prior to beginning a new recruitment cycle. International initiatives are well underway with an emphasis on undergraduate recruitment through goal setting and targeted efforts |
| Diversity | Josephine DeLeon Natasha Kolchevska |  | To be completed by May 2012 | Diversity council had its second meeting and is developing a diversity/excellence plan |
| Goal 10 – Define UNM’s role in fixing New Mexico’s K-12 crisis | Greg Heileman Terry Babbitt Jozi DeLeon | Mark Chisholm – OIR has provided analytical support to the work CEPR is doing with CNM and APS, and can continue to do so. | 1.2012: develop plan for further communication and opportunities for collaboration and alignment with APS and CNM administrators as a start | We have data regarding the success of students at UNM that have attended particular NM high schools. This along with work from CEPR and others may inform the direction of efforts. |
| Goal 11 – Achieve AAU Membership (parsing criteria into increments so we understand what is involved) | Provost’s Cabinet | Mark Chisholm |  | A review of UNM’s standing relating to key AAU membership criteria/metrics was conducted in 2008. We are in the process of reviewing the older report and updating it for the purpose of setting specific goals that might move us towards the benchmarks that might make us eligible. |
| LONG TERM GOALS |  |  |  |  |
| Goal 12 – Improve the perceived value of a UNM Degree | Provost’s Cabinet Deans |  |  |  |
| Goal 13 – Plan for turning diversity into a path-breaking opportunity | Academic Planning Team Jozi DeLeon |  |  | Diversity Council activities |
| Goal 14 – Identify needs of the University and US in 2025 where UNM has the potential for a competitive advantage | Academic Planning Team |  | May 2012 | The aforementioned University Council on Academic Planning (UCAP) will evaluate and recommend long-term goals for the University including where UNM has the potential for a competitive advantage. |